## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US001 | Setup development environment, tools, and database | MUST HAVE | None | ISHITA AGRAWAL | 3- Completed
S1 | S1 | US001 | Design transaction data model and schema | MUST HAVE | Environment setup | ANUSRI | 3- Completed
S1 | S1 | US001 | Create normal and fraudulent datasets | MUST HAVE | Data model | NARESH | 3- Completed
S1 | S1 | US001 | Define rule-based fraud detection conditions | MUST HAVE | Dataset creation | ANSURI | 3- Completed
S1 | S1 | US001 | Design system architecture for all modules | MUST HAVE | Environment setup | ISHITA AGRAWAL | 3- Completed
S1 | S1 | US001 | Create system workflow flowchart | SHOULD HAVE | Architecture design | ISHITA AGRAWAL | 3- Completed
S2 | S2 | US001 | Develop transaction simulation engine | MUST HAVE | Dataset creation | ANUSRI | 3- Completed
S2 | S2 | US001 | Implement fraudulent transaction scenarios | MUST HAVE | Simulation engine | NARESH | 3- Completed
S2 | S2 | US001 | Implement rule-based anomaly detection | MUST HAVE | Rule definition | ANUSRI | 3- Completed
S2 | S2 | US001 | Test detection accuracy with sample data | SHOULD HAVE | Detection implementation | ISHITA AGRAWAL | 3- Completed
S2 | S2 | US001 | Add logging for transactions and alerts | SHOULD HAVE | Simulation engine | ISHITA AGRAWAL | 3- Completed
S2 | S2 | US001 | Optimize system performance and response | COULD HAVE | Testing | ANUSRI | 3- Completed
S3 | S3 | US001 | Integrate machine learning model for detection | MUST HAVE | Detection core | ISHITA AGRAWAL | 3- Completed
S3 | S3 | US001 | Prepare dataset for ML training | MUST HAVE | Dataset creation | ISHITA AGRAWAL | 3- Completed
S3 | S3 | US001 | Evaluate ML model performance | SHOULD HAVE | ML integration | NARESH | 3- Completed
S3 | S3 | US001 | Perform full system integration testing | MUST HAVE | All modules | ANUSRI | 3- Completed
S3 | S3 | US001 | Deploy system to server or cloud | SHOULD HAVE | Testing | ISHITA AGRAWAL | 3- Completed
S3 | S3 | US001 | Validate system accuracy and results | MUST HAVE | Deployment | ISHITA AGRAWAL | 3- Completed
S4 | S4 | US001 | Design fraud monitoring dashboard UI | MUST HAVE | Detection core | ANUSRI | 3- Completed
S4 | S4 | US001 | Develop dashboard with charts and alerts | MUST HAVE | UI design | ISHITA AGRAWAL | 3- Completed
S4 | S4 | US001 | Develop APIs for transaction ingestion | MUST HAVE | API design | NARESH | 3- Completed
S4 | S4 | US001 | Generate fraud detection reports | SHOULD HAVE | Dashboard | ISHITA AGRAWAL | 3- Completed
S4 | S4 | US001 | Test API functionality and integration | SHOULD HAVE | API development | NARESH | 3- Completed
S4 | S4 | US001 | Add filters for dashboard data analysis | COULD HAVE | Dashboard | ISHITA AGRAWAL | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 74 | 15 | 12 | 11 | 9 | 6 | 10 | 5 | 3 | 1 | 0 | 1 | 1 | 0 | 0
SPRINT 1 BACKLOG
US001 | 1 | Project Introduction and Requirement Analysis | 2026-02-04 | 2026-02-19 | Ishita | Others | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US001 | 2 | System workflow and documentation preparation | 2026-02-04 | 2026-02-19 | Ishita | Design | Completed | 8 | 1 | 2 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US001 | 3 | Fraud detection use case identification | 2026-02-20 | 2026-03-02 | Anusri,Ishita,Naresh | Others | Completed | 6 | 2 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US001 | 4 | Transaction data model design and schema creation | 2026-02-20 | 2026-03-02 | Anusri,Ishita,Naresh | Build | Completed | 10 | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US001 | 5 | Creation of normal and fraudulent transaction datasets | 2026-03-03 | 2026-03-16 | Anusri,Ishita,Naresh | Design | Completed | 9 | 2 | 3 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US001 | 6 | Rule-based fraud detection condition definition | 2026-03-03 | 2026-03-16 | Anusri,Ishita,Naresh | Coding | Completed | 12 | 1 | 0 | 1 | 1 | 2 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US001 | 7 | System architecture design for modules | 2026-03-17 | 2026-03-30 | Anusri,Ishita,Naresh | Build | Completed | 14 | 2 | 2 | 0 | 1 | 2 | 2 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0
US001 | 8 | Initial data validation and testing | 2026-03-17 | 2026-03-30 | Anusri,Ishita,Naresh | System Test | Completed | 12 | 4 | 1 | 2 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on fraud detection system requirements | Discussed with mentor and finalized project scope
Sprint 1 | Day 4 | Confusion in transaction data model and workflow | Conducted team discussion and finalized schema and flow
Sprint 2 | Day 6 | Difficulty in building transaction simulation logic | Reviewed examples and refined simulation approach
Sprint 2 | Day 7 | Issues in defining fraud scenarios | Researched fraud patterns and updated scenarios
Sprint 3 | Day 9 | Confusion in rule-based detection implementation | Simplified rules and tested step-by-step
Sprint 3 | Day 12 | Difficulty in dashboard visualization design | Used references and improved UI design
Sprint 4 | Day 16 | Issues integrating ML model with system | Tested integration in phases with mentor support
Sprint 4 | Day 23 | Errors during deployment and system testing | Fixed bugs and performed multiple test runs

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-04 | 2026-02-19 | Anusri ,Ishita , Naresh | Clearly defining fraud detection requirements | Assuming requirements without validation | Participating in team discussions | Conducted meetings with mentor to finalize project scope and workflow
2 | Sprint 2 | 2026-02-20 | 2026-03-02 | Anusri ,Ishita , Naresh | Focusing on transaction simulation development | Delaying implementation tasks | Practicing coding and testing regularly | Completed simulation engine with improved understanding
3 | Sprint 3 | 2026-03-03 | 2026-03-16 | Anusri ,Ishita , Naresh | Designing dashboard and API integration | Rushing UI development without testing | Collaborating with team on implementation | Developed dashboard with proper testing and feedback
4 | Sprint 4 | 2026-03-17 | 2026-03-30 | Anusri ,Ishita , Naresh | Improving ML model integration and deployment | Ignoring performance issues | Debugging and optimizing system | Successfully integrated ML model and deployed system